## Slide 1: Work package 7
Public Awareness and Dissemination
WP Co-ordinators UMA

## Slide 2: Objectives of the WP
To collect the technical, social and economic data required to demonstrate the feasibility of the NEES approach

## Slide 3: Action by Co-ordinators
Develop on-line portal (UMA)
Electronic newsletter (UMA)
Local, regional dissemination (All)
Creating Network of Stakeholders (All)
Local seminars (All)
Setting up final European Seminar (UMA)

## Slide 4: Actions by Paterners
Partner 1, UMA
Partner 2, UCC
Partner 3, CTC
Partner 4, GCU,
Partner 5, ARTEK
Partner 6, U of Ulster
Partner 7, Clar ICH

## Slide 5: Schedule (to end of Project)
Action | -13 J-F | M-A | M-J | J-A | S-O | N-D | -14 J-F | M-A | M-J | J-A | S-O | N-D |  | 
1 | X | X | X | X | X | X | X | X | X | X | X | X |  | 
2 | X | X | X | X | X | X | X | X | X | X |  |  |  | 
3 | X | X | X | X | X | X | X | X | X | X |  |  |  | 
4 | X | X | X | X | X | X | X | X | X | X |  |  |  | 
5 | X | X | X | X | X | X | X | X | X | X |  |  |  | 
6 |  |  |  |  |  |  | X | X | X | X |  |  |  | 

## Slide 6: Cost
partners | P1 | P2 | P3 | P4 | P5 | P6 | P7 | 
Action 1 | 6 000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 
Action 2 | 4 000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 
Action 3 | 4 000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 
Action 4 | 2 000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 
Action 5 | 3 000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 
Action 6 | 9 000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 
 |  |  |  |  |  |  |  | 100 000