## Slide 1: WP1 Project Management and Evaluation
Jose Ospina Project Manager
NEES Project
3rd Irish Partners Meeting
Claremorriss Ireland
27-28th March 2013

## Slide 2: Who are the WP Co-ordinators? (and proposed co-coordinators)
WP1 – Project Management – CCAE (to be led by Jose)
WP2 – Determining Products, Processes, Opportunities & Barriers GCU (to be led by CCAE – Kevin)
WP3 – Benchmarking Best Practices – U of Umea (CCAE as above)
WP4 – Exchange of Best Practice (and long term strategy) – U of Ulster (led by Stuart)
WP5 – Pilot Projects – SKDP ( with NCE as co-coordinators) (led by SKDP Thomas, input from John, Colm NCE - on SEAI Programmes)
WP6 – Training and Support – ARTEK (led by Clar ICH as co-cordinators)
WP7 – Dissemination – U of Umea (led by Clar ICH with input from CCAE)

## Slide 3: Positive progress and achievements to date
4 Full Partner meetings
6 Study Visits (2 x Cork, 2 x Umea 1 x Down 1 x Claremorris)
Criteria for identifying best practices (WP2)
Evaluation Process for BP’s and Expert Panel Evaluation (WP 3)
1st and 2nd Calls for NEES Best Practices (WP3)
6 Best Practices identified, 17 more submitted (WP3)
Launch in Cork City (WP7)
Presentation in Scottish Parliament (WP7)
Significant media coverage of Project (WP7)
Exhibition and publicity materials for NPP Conference (WP7)

## Slide 4: Main problems and short-comings to date
Financial and administrative delays, especially in progress and financial reporting
Unacceptable level of underspend for most Partners
Lack of reported activities from most Partners
Lack of local Best Practices from 1 region (Greenland), low number for Northern Ireland
Lack of activities reported by Partners (e.g. meetings, public events or pilot projects)
Lack of concrete and identifiable results
Lack of clarity in what some Partner are supposed to be doing in the Project

## Slide 5
M | J | J | A | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Events | PM |  |  |  |  | PM | Focus Groups | Focus Groups |  |  |  | PM | Focus Groups |  |  |  |  | PM | Focus Groups |  |  |  |  | PM |  |  |  |  |  | PM |  |  | European Seminar |  |  | Final PM |  |  |  | 
1st Period |  |  |  |  |  | 2nd period |  |  |  |  |  | 3rd period |  |  |  |  |  | 4th period |  |  |  |  |  | 5th period |  |  |  |  |  | 6th period |  |  |  |  |  |  |  |  |  | 
Reports |  |  |  |  |  | 1st Report FLC |  | 1st Report to LP | 1st Report NPP |  |  | 2nd Report FLC |  | 2nd Report | 2nd Report NPP |  |  | 3rd Report FLC |  | 3rd Report LP | 3rd Report NPP |  |  | 4th Report FLC |  | 4th Report LP | 4th Report NPP |  |  | 5th Report FLC |  | 5th Report LP | 5th Report NPP |  |  | Fn Report tFLC |  | Fn Report to LP | Fn Report NPP | 
New Work Programme from now to end of Project

## Slide 6: Underspend Irish Partners
Chart: 
| Staff | Travel and Subs | External Experts | Office Costs (Direct) | Office Costs (Proportional) | Promotion | Equipment | Other Costs | In Kind Costs | TOTAL
CCAE | 0.68 | 0.7881 | 0 | 0 | 0 | 0 | 1 | 0.9263 | 1 | 0.704
SKDP | 0.7282 | 0.9233 | 1 | 0 | 1 | 0.9914 | 1 | 1 | 0.88
NCE | 0.8128 | 0.9567 | 0.61 | 0 | 1 | 1 | 1 | 1 | 0.8859
Clar ICH | 0.5985 | 0.6702 | 0.8443 | 0 | 0.8312 | 0.3801 | 0.8907 | -0.6667 | 0.6903
U of Ulster | 0.6181 | 0.765 | -1 | 0 | 0 | -1 | 0.824 | 1 | 0.6254

## Slide 7: Progress and Possibilities
WP2 and WP3 are proceeding well, and in line for achieving both expenditure and results (e.g. Criteria, Benchmarking and 15 Best Practices)
WP4 has kicked off well, and with sound proposals from U of Ulster and positive proposed Work Programme (to be discussed)
WP5 is also developing well. But we lack an overall picture. There are a number of good proposals (3 x Ireland and 1 x Greenland). But we need at least 2 more Pilots particularly from Partners who have a budget (e.g. SKDP and University of Umea).
WP6 has potential but for the moment only Clar ICH seems to be developing this area, and only locally. We need more concrete proposals over the next months.
WP7 again has potential and some useful actions have been undertaken, but NEES lacks a good dissemination Strategy and more actions with real impact.

## Slide 8: Specific Recommendations
To have a 3rd and possibly a 4th Call. Calls are useful publicity, they help raise our profile, broaden participation and gain knowledge
To have an additional Full Partner Meeting in Cork on the 21st and 22nd of May.
Greenland Partners Meeting in August – consider taking Best Practices to complement training actions?
Public Events to showcase Best Practices in every area. Possibly during Energy Week (end of June). This will raise awareness and take up Promotional Budgets that are currently underspent.
2 more Pilot Project are needed, especially in regions that have Expert and Equipment budgets unspent.
A social media based dissemination strategy that involves all Partners through Linked In, Facebook, Twitter, etc.

## Slide 9: Periodic Technical and Financial Reports
Technical Report 1 (01.05.11-30.09.11) submitted in draft and number of improvements requested.
Financial Report 1 (same period) held up by minor query in Southern and Eastern Regional Assembly – report cannot be finalised until 1st level audit of UCC is completed. A number of Partners opted to not claim. This was agreed by previous desk officer – but not ideal.
NPP/NNEES have requested all Partner to review their INDICATORS for periods 1 and 2 as they have been queried by NPP. Please review and send ASAP to allow update of Technical Report – this will be circulated again for final correction by 31.11.12
Technical Report 2 (01.10.11 – 31.03.12) submitted in draft as not all Partner 1st level audits have been received. Indicators need to be updated, report will circulated again for correction by all by 31.11.12
Financial Report 2 (same period) – Have only received completed 1st level audits from GCU, Clar ICH and Umea – all other reports are outstanding – ARTEK are proposing to not claim for period 2 but to claim for period 2 and 3 together. We will verify with Christopher Parker (NPP desk officer) at the meeting 15.11.12 if this is acceptable. It is imperative that we received 1st level audits for period 2 from ALL Partners ASAP. Technical Report 3 (01.05/12-31.10.12) I have received partner progress reports from Clar ICH, from GCU (note - wrong dates on form)
Financial Report 3 (same period) I have not received any 1st level audits yet this period

## Slide 10: Proposed Action on Periodic Technical and Financial Reports
Given the low level of expenditure and therefore lack of measurable actions, the situation remains CRITICAL
We have still not received any funding and our Project Amendments are now blocked until the 3rd Period Report is submitted
This issue is still priority No. 1 for Project Management.
We are now blocked (in Claim No. 3) by the Southern and Eastern Regional Assembly (Ireland) auditors, who have not responded on 3 1st level claims (UCC, SKDP and NCE). We are doing what we can to get them to move on this
The Project Amendment we submitted are blocked until Claim 3 is submitted
The 4th reporting period is ending at the end of March. Please submit your accounts for Audit to your 1st level control no later than the end of April, and please return the audited accounts to us no later than end of May.
Please ensure accuracy of dates and information given in Reports, both Progress and Financial
Please submit completed partner Progress Reports by the deadlines agreed after each period end. The composite report will be sent back to your for comment/amendment within a month of the period end.
WE CAN DO THIS!

## Slide 11: Reporting Period Deadlines
1st - 01.05.11 – 30.09.12
Claiming: Umea, ARTEK, Clar ICH, CCAE
Not claiming: GCU, Ulster U, SKDP, NCE (must send letter of explanation)
2nd – 01.10.12 – 31.03.12
Claiming 01.10.12 – 31.03.12 – Umea, ARTEK, Clar ICH, CCAE
Claiming 01.05.11-31.03.12 – GCU, Ulster U, SKDP
Not claiming; NCE
3rd – 01.04.12 – 30.09.12 Deadline 01.02.13 (submission still pending due to SERA!)
Claiming 01.05.11-31.03.12 – NCE
Claiming 01.04.12-30.09.12 – Everyone else
4th – 01.10.12 – 31.03.13 Deadline to submit to 1st level 01.05.13 to NPP 01.08.13
5th – 01.04.13 – 30.09.13 Deadline 01.02.14
6th – 01.10.13 – 28.04.14 Deadline 28.10.14

## Slide 12: Note: Match Funding must be included in Claims
Partners are reporting expenditure as coming from their own income and are presenting Claims as if they were 100% NPP grant funded.
This is not acceptable, as 40% of funding has to come from own sources.
Therefore, unless Partners have a very specific source of Match Funding which ha snot yet been taken up (e.g. external grant or other) then please ensure you report around 40% of your expenditure as Match Funded.