## Slide 1: Natural Energy Efficiency and Sustainability (NEES) in Existing Buildings: WP 2 Determining Products, Processes, Opportunities & Barriers
Project Meeting No 4, New Castle, Co Down 16-11-2012

## Slide 2: Outline
Report on Indicators and Evaluation Process
Report of NEES Best Practice (BP) Call 1
Report on NEES BP Call 2
Future Calls and Expert Panel Meeting & Evaluations
Next Steps
<number>
NEES
Notes: <number>

## Slide 3: WP 2 Key Activities
Develop and define headline indicators
Select and collate NEES product, processes and services
Establish the supply and demand for NEES product, processes and services across the partner regions
Identify 2-3 examples of best practice from each region
<number>
NEES
Notes: <number>

## Slide 4: Indicators & Evaluation Process

## Slide 5: The process
Potential ‘NEES’ manufacturers / service providers register on NEES website using a simple PQQ
If they are ‘Natural’ and for ‘Energy Efficiency’ they get send either ‘product’ or ‘service’ questionnaire
Questionnaire submissions are collated to sent to an ‘Expert Panel’ for evaluation and selection of ‘Best Practice’
The process is repeated every 6 months or so until a sufficient number of ‘Best Practices from the NPP are identified
<number>
NEES
Notes: <number>

## Slide 6: Indicators (Questionnaire Survey)
28 questions covering
  Demographic info
  Key criteria info (‘Natural’ or recycled, contribution to energy efficiency, sustainability criteria)
  Barriers and opportunities
  Market/cost/enterprise info
Call 1: 01 Jun to 31 Jul 2012
  27 PQQ successes leading to 16 full questionnaire submissions
  6 submissions selected as best practices (5 from Ireland + 1 Scotland)
<number>
NEES
Notes: <number>

## Slide 7: Experience so far
Questionnaire has been revised and simplified, taking into account the lessons from Call 1 and comments from the expert panel
Questionnaire now matches the Expert Panel selection criteria
  Resource efficiency
  Environment & health
  Sustainability
  Enterprise
  Scalabilty
Two versions (Products & Services) developed to facilitate easy entry of both
<number>
NEES
Notes: <number>

## Slide 8: Best Practice Call 2

## Slide 9: Call 2 now open!
Launched the call and intro to Project at the Scottish Parliament on 27.09.2012
Initial problems with the website sorted
We will now extend it to end of Jan 2013
EP will meet in Scotland in Feb 2013 (date tba)
BP selections to be announced by end Feb ‘13
<number>
NEES
Notes: <number>

## Slide 10: Future calls

## Slide 11: Best Practice Selection
Project proposal suggests up to 15 BPs
We will certainly need Call 3, perhaps also Call 4?
Call 3 could be Sweden-based (?) to encourage greater participation from Nordic countries
Call 4 to be decided if needed?
We now have 6 BPs (5 products and 1 service); need to keep the mix right
Geographical coverage issues
<number>
NEES
Notes: <number>

## Slide 12: Next Steps

## Slide 13: GCU steps
Complete Call 2 and BP selection (end Feb ‘13)
Identify supply/demand issues for BPs relevant to Scottish NPP regions (Apr ‘13)
Identify and facilitate ‘Demonstrator Projects’ (negotiations with Aps underway) – summer 2013
Promotional events – promoting BPS in Scottish NPP regions (late 2013)
Teaching/Practice Note preparation and dissemination (rest of the project)
<number>
NEES
Notes: <number>

## Slide 14
Dr Rohinton Emmanuel Dr Craig Thomson Dr Keith Baker
School of Built & Natural Environment,
Glasgow Caledonian University
70 Cowcaddens Road
Glasgow G4 0BA
Tel: 0141 331 3217
Email: Rohinton.Emmanuel@gcu.ac.uk Craig.Thomson@gcu.ac.uk Keith.Baker@gcu.ac.uk
Further information: