## Slide 1: Work package 3
Benchmarking Best Practice
WP Co-ordinators UMA

## Slide 2: Objectives of the WP
To identify products and processes more likely to be sustainable and beneficial in each region.
To select the of Best Practice in products and services currently available in he NPP region, with technical and other details and case study documentation.

## Slide 3: Action by Co-ordinators
1. Selection of 15 Products and Sevices, All (expert group, UCC co-ordination) 2nd call Oct 1-Dec 1, 3rd call March -May
2. Collection of data and uploading on portal, UMA
3. Productions of posters, UMA
4. Case study reports, UMA

## Slide 4: Actions by Paterners
Partner 1, UMA
Partner 2, UCC
Partner 3, GCU
Partner 4, University of Ulster
Partner 5, Artek

## Slide 5: Schedule (to end of Project)
Action | -13 J-F | M-A | M-J | J-A | S-O | N-D | -14 J-F | M-A | M-J | J-A | S-O | N-D |  | 
1 | X |  |  | X |  |  |  |  |  |  |  |  |  | 
2 |  | X | X |  |  |  |  |  |  |  |  |  |  | 
3 |  | X |  |  | X |  |  |  |  |  |  |  |  | 
4 |  | X |  |  | X |  |  |  |  |  |  |  |  | 

## Slide 6: Cost
partners | P1 | P2 | P3 | P4 | P5 |  |  | 
Action 1 | 5000 | 9000 | 5000 | 5000 | 5000 |  |  | 
Action 2 | 3000 | 1000 | 1000 | 1000 | 1000 |  |  | 
Action 3 | 3000 | 1000 | 1000 | 1000 | 1000 |  |  | 
Action 4 | 3000 | 1000 | 1000 | 1000 | 1000 |  |  | 
 |  |  |  |  |  | 50 000 |  |