## Slide 1: Progress of WP6: Support and Training
Arctic Technology Center,
Technical University of Denmark
Nov. 17, 2012, New Castel, Co. Down, Northern Ireland

## Slide 2: The Aim of Training
To transfer knowledge and skills of NEES Best Practices to different NPP regions
To provide accredited training modules
Target groups: producers, installers, housing associations, municipalities and private owners

## Slide 3: Process of Training Development
Training template design
Partners fill in local information respectively
ARTEK will organize all the information and the final training modules
Get the training accredited in each region
Promote the NEES training on NEES website, possibly on partners’ websites
Training package transferred to local energy consultancy companies, municipalites and research and education institutions
Survey of training needs

## Slide 4: Actions by ARTEK
Design survey of training needs
Send out invitations for answering survey in Greenland
Design training template
Organize all the information after input by each partner
Get training accredited in Greenland or Denmark
Promote the NEES training

## Slide 5: Actions by partners
Send out invitations for answering survey in partner region
Partners fill in local information respectively
Get the training accredited in each region
Help with promotion of the NEES training

## Slide 6: Timetable for Training Development
 | 2012 |  | 2013 |  |  |  |  |  |  |  |  |  |  |  | 2014 |  |  | 
 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4
Survey | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Template design |  |  |  | x | x | x |  |  |  |  |  |  |  |  |  |  |  | 
Information input |  |  |  |  |  |  | x | x | x |  |  |  |  |  |  |  |  | 
NEES meeting Greenland |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  | 
Organize |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  |  |  | 
Training accredited |  |  |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  | 
Promotion |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x | x | x

## Slide 7: Training
Training will be carried out in 3 modules: Technical, Business, Social
Trainees could choose one or more modules according to their needs

## Slide 8: Survey for Training Needs
Aim of the survey: to figure out what trainees want to know about the product
Survey to be put on NEES.org
Partners send out invitations

## Slide 9: Currently available training programmes
Training currently available from Partners, including training template, existing trainings, etc.

## Slide 10: Training Template
ARTEK will finish the template
Each partner will fill in information according to different BPs (Best practice), CSs (case study), DPs (demonstration project) from different NPP regions.

## Slide 11: Module A: Technical Issues
 | Content |  | Duration
Theoretical introduction | Basic knowledge about climate change, energy efficiency in buildings, energy assessment, benefits of low energy buildings, environmental impact, LCA, etc. |  | 2 -3 hrs
NEES Best Practices | Technical data and product performance (to be provided by producers) | LCA assessment U-value Airtightness Environmental issues (ex. Embodied energy, CO2 emissions, etc.) Fire safety Acoustical comfort Maintenance requirement | 6 -10 hrs
 | Samples to show in class (to be provided by producers) Case Studies (to be provided by producers) How to install (installers’ manual) (texts, technical drawings, drawings of details, pictures and videos, to be provided by the producers) Why is it applicable in NPP regions? Transferability (WP4) |  | 
Demonstration Project | Videos showing the construction process, details, technical drawings, drawing of details, pictures, energy efficiency evaluation before and after retrofitting |  | 3 -5 hrs

## Slide 12: Theoretical Introduction
Simple introduction
Necessary for private house owners, but will be determined by the survey result

## Slide 13: NEES Best Practices
Case studies (to make the course more interesting and inductive)
Samples to show in class
Technical data and product performance
How to install (installers’ manual) (texts, technical drawings, drawings of details, pictures and videos
Why is it applicable in NPP regions?

## Slide 14: NEES Demonstration Projects
Videos showing the construction process, details
Technical drawings
Drawing of details, pictures
Energy efficiency evaluation before and after retrofitting

## Slide 15: Module B: Business issues
Target group: NEES Best Practice providers
Business planning, marketing, etc.
Provide advices for the trainees to know how to promote their products and services inside and outside the NPP region.
To be combined with U of Ulster Marketing Model?
Duration: 1 -3 hrs

## Slide 16: Module C: Social issues
Fuel poverty, affordability, consultation and participation of social enterprise, etc.
For the trainees to convince their clients and local municipalities
Duration: 1 -3 hrs

## Slide 17: Training exchange & partner meeting in Greenland in Aug. 2013
After filling in information respectively, partners discuss about the training template
The best season in Greenland, welcome!!!

## Slide 18: Support
To help the producers, installers and service bodies, and to the end users of the products and services
To facilitate the application of NEES technologies inside and outside the NPP region.
Support will be done through NEES website and database.

## Slide 19
Thanks!