## Slide 1: Work Package 4 – Transfer of Best Practice
Sisimuit, Greenland
August 2013

## Slide 2: Site Visits
Completed
Advanced Timbercraft Ltd
FH Wetland Systems
Mud and Wood

## Slide 3: Recent Site Visits
The Hollies
ECOCEL

## Slide 4: Site Visits
To be completed
Locate Architects
Ecological Architecture
Enviroglass
Inzievar Woodlands
Green Roofs Ireland
Martinsons Gluelam
Martinsons Xlam
Masonite Beams
SWECO

## Slide 5: Virtual Meeting Software
Adobe Connect software procured
Meetings can be scheduled by both the University of Ulster and University College Cork
Monthly service plan
Potential for regular progress meetings

## Slide 6: N. Ireland Conference - 17th October 2013
Potential speakers:
NEES Partners
MP’s
Housing Executive
Best Practice Case Studies
Tom Woolley
Bank- Bank of Ireland/Danske

## Slide 7
Task 4.1 – Development and implementation of questionnaire to facilitate technical, economic and social evaluation |  |  | 
Deliverables: | Partners Responsible: | Due Date: | Status:
4.1.1 Conduct research to facilitate the development of business model questionnaire | U of Ulster | Thursday 31st January 2013 | Complete
4.1.2 Produce draft business model questionnaire Industry Expert to pilot Further refinement | U of Ulster | Thursday 28th February 2013 | Complete
4.1.3 Questionnaire reviewed and feedback provided by partners | All Partners | Thursday 28th March 2013 | Complete

## Slide 8
Task 4.2 – Review by Local Focus Groups of best practices identified in all regions and preparation of presentations and consultation material to disseminate locally in order to establish local demand and feasibility |  |  | 
Deliverables: | Partners Responsible: | Due Date: | Status:
4.2.1 Establish Local Focus Groups | UU, Clar ICH, GCU, ARTEK, Umea, | Wednesday 31st July 2013 | ?
4.2.2 Local Focus Groups to review best practices | UU, Clar ICH, GCU, ARTEK, Umea, | Friday 30th August 2013 | Ongoing
4.2.3 Develop presentations and consultation materials for dissemination purposes – adapt for the partner regions | UU, Clar ICH, GCU, ARTEK, Umea, | Wednesday 31st July 2013 | ?
4.2.4 Local focus groups will provide quality assurance checks of T4.2.3 outputs | UU, Clar ICH, GCU, ARTEK, Umea, | Friday 30th August 2013 | Ongoing

## Slide 9
Task 4.3 – Consultation with stakeholders in each region, to establish appropriateness of selections and other economic, social and environmental implications |  |  | 
Deliverables: | Partners Responsible: | Due Date: | Status:
4.3.1 Identify local stakeholders for consultation regarding best practice selections | UU, Clar ICH, GCU, ARTEK, Umea | Friday 30th August 2013 | Ongoing
4.3.2 Consult with stakeholders in each region regarding transferability of best practice examples | U of Ulster/ Clar ICH, GCU, ARTEK, Umea | October 2013 | Ongoing
4.3.3 Produce a draft report outlining the business feasibility of selected best practice transfers | U of Ulster | August 2013… | Delayed

## Slide 10
Task 4.4 - Study visits to projects where products and services are demonstrated to establish feasibility for other regions |  |  | 
Deliverables: | Partners Responsible: | Due Date: | Status:
4.4.1 Visit best practice examples which have been selected and assess them using the completed Questionnaire from T4.1 | U of Ulster/ All Partners | August 2013 | Ongoing
4.4.2 Provide draft report on findings from initial work | U of Ulster | September 2013 | Ongoing
4.4.3 Identify other working examples which fit best practice criteria Conduct study visits Analyse using Questionnaire developed in T4.1 | U of Ulster/All Partners | November 2013 | Ongoing

## Slide 11
Task 4.5 - Formulate action plans to disseminate best practice in implementing pilots in partner regions |  |  | 
Deliverables: | Partners Responsible: | Due Date: | Status:
4.5.1 Document and disseminate findings from WP5 through; summary reports, photographs, videos online decision making support tool- cost, suitability, usability | All Partners | March 2014 | Ongoing
4.5.2 Host conference/exhibition to disseminate outputs | U of Ulster | January-April 2014 | Ongoing