## Slide 1: WP1 Project Management and Evaluation
Jose Ospina Project Manager
NEES Project
Final Partners Meeting
Umea, Sweden
27th March 2014

## Slide 2: Format for Final Partner’s meeting (and proposed rdiscussion leads)
WP1 – Project Management – CCAE (led by Jose)
WP2 – Determining Products, Processes, Opportunities & Barriers - GCU (led by Rohinton)
WP3 – Benchmarking Best Practices – U of Umea – (led by Geza)
WP4 – Exchange of Best Practice and long term strategy) – U of Ulster (led by Derek)
WP5 – Pilot Projects – SKDP - (led by Raoul Empey)
WP6 – Training and Support – ARTEK-( led by Tom W)
WP7 – Dissemination – U of Umea (led by Geza)

## Slide 3: Key Positive progress and achievements to date
7 Full Partner meetings (WP1)
11 Study Visits (2 x Cork, 2 x Umea, 1 x Down 2 x Claremorris, 4 Sisimiut) (WP1)
5 point Criteria for identifying best practices (WP2)
3 Calls for NEES Best Practices, Expert Evaluation meetings &15 Best Practices selected and profiled (WP3)
Feasibility studies of best practices carried out (WP4)
Bids made to NPP Programmed and Horizon 2020 Programmed(WP4)
5 Pilot Projects and 3+ training pilots (WP5)
Vocational Training Modules and Training Guide produced (WP6)
12 + public events and presentations in all Partner regions. (WP7)
Significant web site visits (150,000 to date) and e-newsletters sent out and multiple media coverage (WP7)

## Slide 4
M | J | J | A | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Events | PM |  |  |  |  | PM | Focus Groups | Focus Groups |  |  |  | PM | Focus Groups |  |  |  |  | PM | Focus Groups |  |  |  |  | PM |  |  |  |  |  | PM |  |  | European Seminar |  |  | Final PM |  |  |  | 
1st Period |  |  |  |  |  | 2nd period |  |  |  |  |  | 3rd period |  |  |  |  |  | 4th period |  |  |  |  |  | 5th period |  |  |  |  |  | 6th period |  |  |  |  |  |  |  |  |  | 
Reports |  |  |  |  |  | 1st Report FLC |  | 1st Report to LP | 1st Report NPP |  |  | 2nd Report FLC |  | 2nd Report | 2nd Report NPP |  |  | 3rd Report FLC |  | 3rd Report LP | 3rd Report NPP |  |  | 4th Report FLC |  | 4th Report LP | 4th Report NPP |  |  | 5th Report FLC |  | 5th Report LP | 5th Report NPP |  |  | Fn Report tFLC |  | Fn Report to LP | Fn Report NPP | 
New Work Programme from now to end of Project

## Slide 5: Progress and Possibilities
WP2 and WP3 achieved outcomes (e.g. NEES Criteria, Benchmarking and 15 Best Practices).
WP4 carried out business feasibilities, final report and conclusions pending, and how this will be followed up
WP5 seems positive with over 5 Pilot projects (4 in Ireland, 1 in Greenland). Also a number of smaller “training” projects. These must be well documented in final evaluation of impacts.
WP6 vocational training course and guidelines under development. We do not have tome to deliver full vocational programmed, but specific training has been carried out by Cloyne Pilot in Cork (more to be revealed), as well as Clar ICH and SKDP training network.
WP7 dissemination has been patchy but picked up towards the end particularly with GCU’s Inverness event. We still have tome to make one ;last effort on the basis of results web site, film and final reports and possibly presentations at other events? .

## Slide 6: Final actions – Hat trick is possible!
Get complete information from Best Practices for web site, final report and dissemination
Get complete information on Pilot Projects, particularly any technical information available
Review progress on Best Practice feasibilities and Focus Groups
Finalise vocational training package and investigate potential delivery plan
Take up remaining Expert and Equipment budget where possible.
Dissemination strategy for end of Project Is need. Aimed at target audiences and coordinated, to includes all Partners through all media available. Inc. Linked In, Facebook, Twitter, etc.
Tale up any remaining Promotional Budgets that are currently underspent
Partners need to be prepared to succinctly document their experiences and outcomes from the Project.

## Slide 7: NEES Project Financial Forecast at 27.03.14

## Slide 8: Periodic Technical and Financial Reports
Technical Report 1 (01.05.11-30.09.11) submitted in final form to NPP.
Financial Report 1 (same period) now with Managing Authority in Sweden for approval. Held up by bureaucratic delays (having resolved minor queries). A number of Partners opted to not claim. This is not ideal.
Technical Report 2 (01.10.11 – 31.03.12) submitted in final form to NPP
Financial Report 2 (same period) now with Managing Authority in Sweden for approval. Held up by bureaucratic delays (having resolved minor queries). A number of Partners opted to not claim. This is not ideal.
Technical Report 3 (01.04.12-30.09.12) submitted in final form to NPP
Financial Report 3 (same period) submitted to NPP on 18.06.13, pending payment
Technical Report 4 (01.10.12/31.03.13)Submitted to NPP just after deadline
Financial Report 4 (same period) all Partners except NCE included in Account . Pending payment. With Payment 3.
Technical and Financial Report 5 (01.04.13-30.09.13) - Submitted just after deadline . No claim by NCE. Pending payment.
Technical and Financial Report 6 (Final) (01.10.13- 28.04.13) – Partner account to 1st level control by 31st of May 2014, audited 1st level accounts by 30th June to CCAE, Final Report to NPP by 28.10.14

## Slide 9: Note: Match Funding must be included in Claims
Partners are reporting expenditure as coming from their own income and are presenting Claims as if they were 100% NPP grant funded.
This is not acceptable, as 40% of funding has to come from own sources.
Therefore, unless Partners have a very specific source of Match Funding which has not yet been taken up (e.g. external grant or other) then please ensure you report around 40% of your expenditure as Match Funded.

## Slide 10: Overview Final Reporting Package
Final Financial Report
Statement of Expenditure
Certificate of Expenditure
Final Project Claim
Final Administrative Report
General information
Project activities
Results
Indicators
Project financial information
Project management and partnership dynamics
NPP horizontal principles
Project communication
Changes
Additional information
Final Content Report
Introduction
Project story
List of project outcomes
List of producers/providers
Testimonials
Visualisation
Contact Details
Product/service factsheet(s)

## Slide 11: Final Content Report
Final Financial Report
Statement of Expenditure
Certificate of Expenditure
Final Project Claim
Final Administrative Report
General information
Project activities
Results
Indicators
Project financial information
Project management and partnership dynamics
NPP horizontal principles
Project communication
Changes
Additional information
Final Content Report
Introduction
Project story
List of project outcomes
List of producers/providers
Testimonials
Visualisation
Contact Details
Product/service factsheet(s)
Purpose: to collect information for wide publication on a web based platform in order to be able to visualise project outcomes
Target group: end users/beneficiaries
Structure:
  Project stories
  Product/service factsheets:
    Product/service name
    Key words
    Functionality
    Target group(s)
    Attributes
    References
    How to get the solution
    Visualisation

## Slide 12: Professional standard
  Rationale: information should allow for versatile use
  Style requirements:
    Plain English, written for the target group
    Coherent, concise, inverted pyramid
    Archive friendly
  Criteria for audiovisual materials
    Product: picture(s). Optional: graph(s), animation/video
    Service: graph(s) explaining process/model. Optional: picture(s), animation/video
  You can use existing materials if they meet the criteria
  If necessary, hire professionals or look for in-house resources

## Slide 13: Final Content Report - Rationale
Rationale: to collect information in order to be able to visualise project outcomes for wide publication
  The Programme needs to demonstrate tangible outcomes (accountability, sharing solutions and making case for future NPP)
  So far not much concrete information available  final report is the last opportunity
  Template will facilitate information gathering about concrete project outcomes
Information will be collected once at project closure
  Information remains static
  Reduced need for further information requests , although LP responsible for providing information for up to 5 years

## Slide 14: How will the information be used?
Online web solution
  To display project outcomes in an attractive online format for anyone to view and share
  Target group: end users/beneficiaries
  Static information: project stories and project outcomes
  Dynamic information: news articles highlighting major achievements, possibilities to interact and build networks through social media
Possible other uses of the information
  Thematic publications
  Annual and Final Implementation Report NPP 2007-2013

## Slide 15: Expenditure only related to closure
After the final date for project activities only expenditure related to the closure of the project can be accepted.
This means:
  No activities such as conferences, seminars and travel costs are eligible, except for activities by invitation by the NPP, in which the NPP will outline if this is eligible as a closure activity, such as a Lead Partner seminar.
  All expenditure should therefore be directly connected to the final report, such as writing the final report, compiling final project claim, etc.

## Slide 16: Eligible closure costs
No costs incurred after final certification can be reimbursed by the programme.
The following expenditure categories can be acceptable:
  Staff costs including social contributions - Only costs for staff actually involved in the project closure.
  External experts - If involved in writing the final report or producing relevant materials.
  Office costs (directly allocated)
  Office costs (distributed proportionally)
  Other costs (charges for transnational transactions, bank charges for account closure/administration, costs for First Level Control, etc.)
  The only cost that needs a special procedure is the last invoice for First Level Control. In order to get these costs certified, partners have to get the audit firms to pre-invoice (á conto) them and include these costs in their Statements of Expenditure for certification.
Please note that it is up to each FLC to judge if costs are reasonable in relation to project closure. The programme administration cannot possibly set limits for closure expenditure as this will differ between partners and countries.

## Slide 17: Final suggested actions
Last chance for project expenditure – Please spend your budgets…
Please submit your accounts by June 2014
Actions taken to consolidate and leave a legacy are crucial:
Full details of the 15 Best Practices
Reports from major Project events (including Papers from this Seminar)
Reports (especially impact assessments) from Pilot Projects (e.g. Life Cycle Assessment of Cloyne Pilot)
The Vocational Training Modules and Training Guide
The Results Web Site
The Final Content Report (Partner editorial input welcome)

## Slide 18: Thanks!